## Dashboard
EverAfter — Wedding Budget Suite
Sarah & James ¦ June 14, 2026 ¦ Grandview Estate, Napa Valley
WEDDING COUNTDOWN
4 |  | 12 |  | 36
DAYS |  | HOURS |  | MINUTES
BUDGET SUMMARY
Total Budget |  | Committed |  | Paid |  | Remaining
$50,000 |  | $42,350 |  | $28,100 |  | $7,650
Original estimate |  | 84.7% allocated |  | 56.2% of budget |  | Available to spend
UPCOMING PAYMENTS |  |  | RECENT ACTIVITY
Category | Due Date | Amount | Date | Event | Note
Photography | Due in 2 days | $3,200 | Today, 9:30 AM | Final guest count confirmed | 142 attending (was 150)
Florist | Due in 5 days | $2,800 | Yesterday | Seating chart finalized | Saved $400 by reducing table count
Transportation | Due in 8 days | $1,200 | Jun 8 | Catering headcount due | Pending — waiting on 3 RSVPs

## Budget
BUDGET BREAKDOWN
Category | Details | Budget | Spent | % Used
Venue & Rentals | Grandview Estate, chairs, tables, linens | 15000 | 15000 | 100%
Catering & Bar | $105 per person × 142 guests | 15000 | 14910 | 99.4%
Photography & Video | 8 hours coverage, 2 shooters | 6000 | 4800 | 80%
Florist & Decor | Bouquets, centerpieces, arch | 4000 | 3000 | 75%
Music & Entertainment | DJ + live ceremony quartet | 3000 | 1800 | 60%
Attire & Beauty | Dress, suit, alterations, hair & makeup | 3000 | 2700 | 90%
Stationery & Gifts | Invites, programs, favors | 1300 | 650 | 50%
Miscellaneous | Tips, emergency fund, marriage license | 1700 | 490 | 28.8%
TOTAL |  | 49000 | 43350 | 88.47%

## Vendors
VENDOR TRACKER
Vendor | Type | Status | Notes
Grandview Estate | Venue | Booked | Deposit paid, final due 2 weeks before
Lumiere Photography | Photography | Booked | 8 hours, 2 shooters
Harvest Table Catering | Catering | Booked | 142 guests, $105/head
Petal & Stem | Florist | Pending | Awaiting final quote
Soundwave DJs | Entertainment | Quoted | DJ + ceremony quartet package
Napa Classic Cars | Transportation | Quoted | Vintage Rolls option

## Guests
GUEST LIST
SUMMARY |  | GUEST DETAILS
Invited | 200 | Name | Group | Status | Dietary
Attending | 142 | Eleanor & Robert Whitfield | Family | Attending | None
Declined | 8 | Marcus Chen | Friend | Attending | Vegetarian
Pending | 50 | Alexandra Ross | Friend | Attending | None
Cost Per Head | $148 | David & Susan Park | Family | Attending | Gluten-free
|  | Jennifer Blake | VIP | Attending | Vegan
|  | Thomas & Marie Laurent | Family | Declined | —
|  | Jordan Smith | Friend | Pending | —

## Timeline
WEDDING DAY TIMELINE
Time | Event | Location / Notes | Status
8:00 AM | Hair & Makeup | Bridal suite — 4 artists on site | Done
11:00 AM | Photographer Arrives | Detail shots, getting-ready candids | Scheduled
1:00 PM | First Look | Garden terrace — private moment | Scheduled
2:30 PM | Ceremony | Grandview lawn — 30 minutes | Scheduled
3:00 PM | Cocktail Hour | Terrace & garden — passed hors d'oeuvres | Scheduled
4:30 PM | Reception | Grand ballroom — dinner, speeches, dancing | Scheduled
10:00 PM | Sparkler Send-off | Front circle drive | Scheduled